{"text_format":"5","workbook":"xlsx","n_sheets":8,"sheets":["UNDERWAY WORKFLOW TASK LIST","PROJECT WRAP-UP","DN59","DN58","DN57","DN56","DN55","YYYY-DDD blank"],"not_rendered":{"images":2},"read":"whole","wrapped":"gz","date_system":"1900"}

{"sheet":"UNDERWAY WORKFLOW TASK LIST","index":0,"n_rows":13,"n_cols":6,"rows_kept":13,"merged":[[0,0,0,5],[1,0,1,5],[11,0,12,0]]}
["NEW UNDERWAY MBES PROCESSING WORKFLOW"]
["If time allows, you can complete all of the Processing checklist items in the working project log. \nHowever, this shortened version of the processing workflow is designed to be manageable while underway on a busy cruise.\n\nTime estimates are listed next to tasks. These time estimates are broken down into hands-on time and hands-off time. \nStill use the working project log to keep track of progress. \nPlease feel welcome to adjust this workflow as needed!"]
["Task",null,"Hands-on time MIN [min]","Hands-on time MAX [min]","Hands-off time MIN [min]","Hands-off time MAX [min]"]
["Complete acquisition log from previous day, \nstart acquisition log for next day",null,3,5,"-","-"]
["Transfer raw files to appropriate locations on the science drive (POS, MBES, SV)",null,3,5,10,15]
["Process in Charlene",null,2,5,30,45]
["Create surface in Caris",null,2,5,5,10]
["*OPTIONAL*\nSpot clean if necessary (any big, obvious blowouts in the surface), \nrecompute surface when finished",null,15,60,5,10]
["Calculate area mapped",null,3,5,"-","-"]
["Create GeoTIFFs and record extents",null,5,10,"-","-"]
[]
["Time Totals",null,{"$f":"SUM(C4:C10)","v":33},{"$f":"SUM(D4:D10)","v":95}]
[{"$nulls":4},{"$f":"SUM(E4:E10)","v":50},{"$f":"SUM(F4:F10)","v":80}]

{"sheet":"PROJECT WRAP-UP","index":1,"n_rows":58,"n_cols":42,"rows_kept":58,"merged":[[2,1,2,63],[4,1,4,24],[5,1,5,63],[8,1,8,14],[8,21,8,28],[8,29,8,45],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,45],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,45],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,45],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,45],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,45],[14,1,14,7],[14,8,14,14],[14,21,14,28],[14,29,14,45],[15,1,15,7],[15,8,15,14],[16,1,16,7],[16,8,16,14],[20,1,20,64],[22,1,22,7],[22,9,22,15],[22,17,22,23],[22,25,22,31],[22,33,22,39],[22,41,22,47],[23,1,24,7],[23,8,24,8],[23,9,24,15],[23,17,23,23],[23,25,23,31],[23,33,24,39],[23,40,24,40],[23,41,24,47],[25,1,25,7],[25,9,25,15],[25,33,26,39],[25,40,26,40],[25,41,26,47],[26,1,28,7],[26,8,28,8],[26,9,28,15],[27,33,28,39],[27,40,28,40],[27,41,28,47],[29,1,32,7],[29,8,32,8],[29,9,32,15],[29,33,32,39],[29,40,32,40],[29,41,32,47],[48,1,49,8],[48,9,49,28],[50,1,50,8],[50,9,50,28],[52,1,52,8],[52,9,52,28],[53,1,53,8],[53,9,53,28],[54,1,54,8],[54,9,54,28],[55,1,55,8],[55,9,55,28],[57,1,60,8],[57,9,60,28]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"Project Summary and Project Completion Checklist"]
[null,"          This page of the document is to be completed at the end of the project. This page serves as a checklist for final project deliverables and as a summary of the total project's mapping operations."]
[]
[null,"General Project Information",{"$nulls":19},"Project Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Dates of Mapping",{"$nulls":7},"2/25/2022-2/28/2022"]
[null,"Project Number",{"$nulls":6},"RB2201",{"$nulls":12},"Julian Day Numbers",{"$nulls":7},"056-059"]
[null,"Project Name",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},1148.2]
[null,"Chief Scientist ",{"$nulls":19},"Total Mapped (nm^2)",{"$nulls":7},1896.2]
[null,"Organizations Involved",{"$nulls":19},"Aprox. Geographical Region",{"$nulls":7},"Southeast coast of United States (transit around Florida)"]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Ops General Description",{"$nulls":7},"No ops"]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Comments",{"$nulls":7},"Transit from Pascagoula, MS to Charleston, SC"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC"]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Deliverable Preparation",{"$nulls":7},"Comments",{"$nulls":7},"Deliverable Submission",{"$nulls":7},"Comments",{"$nulls":7},"Ship Wrap-up",{"$nulls":7},"Comments"]
[null,"DR Memo or Summary written",{"$nulls":7},"N/A",{"$nulls":7},"Data package submitted",{"$nulls":7},"submission to NCEI",{"$nulls":7},"Total project GeoTIFF created with map background",{"$nulls":6},"x"]
[]
[null,"DR appendices compiled",{"$nulls":7},"N/A",{"$nulls":23},"All project files organized on ship network",{"$nulls":6},"x"]
[null,"Acquisition and processing logs concatenated",{"$nulls":7},"N/A"]
[{"$nulls":33},"All project files on ship network backed up",{"$nulls":6},"x"]
[]
[null,"Final check completed of data in submission directories and directory structure",{"$nulls":7},"N/A",{"$nulls":23},"Working project log completed",{"$nulls":6},"x"]
{"$rows_empty":15}
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the project's coverage here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name",{"$nulls":7},"RB2102_164-206_32m_COMBINED.tif\nRB2102_164-206_32m_COMBINED_withGEBCO.tif"]
[]
[null,"file location",{"$nulls":7},"Z:\\EM122\\Reference GeoTIFFs\\2021\\RB-21-02"]
[]
[null,"NW extent of coverage",{"$nulls":7},"28.8713 N x 87.2592 W"]
[null,"NE extent of coverage",{"$nulls":7},"31.6028 N x 79.5925 W"]
[null,"SE extent of coverage",{"$nulls":7},"24.7714 N x 79.8348 W"]
[null,"SW extent of coverage",{"$nulls":7},"24.1317 N x 83.1636 W"]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes",{"$nulls":7},"Transit from Pascagoula, MS to Charleston, SC."]

{"sheet":"DN59","index":2,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date",{"$nulls":7},"2022-02-28"]
[null,"Project Number",{"$nulls":6},2201,{"$nulls":12},"Julian Day Number",{"$nulls":7},59]
[null,"Project Name",{"$nulls":6},"Transit to Charlestom",{"$nulls":12},"Local Time Zone",{"$nulls":7},-5]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %",{"$nulls":7},54]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},61]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Total Mapped (nm^2)",{"$nulls":7},36.11]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Aprox. Geographical Region",{"$nulls":7},"South of Charleston, SC"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28",{"$nulls":12},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC",{"$nulls":12},"Comments",{"$nulls":7},"Eliminated lines 0439-0495 due to shallow depths. Some lines did not georeference and had no error message displayed in the Charlene processing log. "]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":6},"x",{"$nulls":8},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":6},"x",{"$nulls":8},"Processed in Charlene? (Y/N)",{"$nulls":6},"y",{"$nulls":8},"Finalized surface created",{"$nulls":6},"x"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported",{"$nulls":6},"x"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked",{"$nulls":6},"x"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created",{"$nulls":6},"x"]
[{"$nulls":33},"Data cleaned",{"$nulls":6},"x"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed",{"$nulls":6},"x"]
[]
[{"$nulls":33},"Area mapped calculated",{"$nulls":6},"x"]
[{"$nulls":33},"GeoTIFF created and extents recorded",{"$nulls":6},"x"]
[]
[{"$nulls":33},"GSFs exported",{"$nulls":6},"x"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name",{"$nulls":7},"RB2201_059_UTM17N_80m_GEBCO.tif"]
[null,"file location",{"$nulls":7},"Z:\\EM122\\Reference GeoTIFFs\\2022\\RB-22-01_Charleston"]
[]
[null,"N extent of coverage",{"$nulls":7},"31.6130 N x 79.5948 W"]
[null,"S extent of coverage",{"$nulls":7},"31.0118 N x 79.5962 W"]
[]
[]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]

{"sheet":"DN58","index":3,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date",{"$nulls":7},"2022-02-27"]
[null,"Project Number",{"$nulls":6},2201,{"$nulls":12},"Julian Day Number",{"$nulls":7},58]
[null,"Project Name",{"$nulls":6},"Transit to Charlestom",{"$nulls":12},"Local Time Zone",{"$nulls":7},-5]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %",{"$nulls":7},100]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},316]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Total Mapped (nm^2)",{"$nulls":7},558.23]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Aprox. Geographical Region",{"$nulls":7},"East of Florida"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28",{"$nulls":12},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC",{"$nulls":12},"Comments"]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":6},"x",{"$nulls":8},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":6},"x",{"$nulls":8},"Processed in Charlene? (Y/N)",{"$nulls":6},"y",{"$nulls":8},"Finalized surface created",{"$nulls":6},"x"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported",{"$nulls":6},"x"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked",{"$nulls":6},"x"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created",{"$nulls":6},"x"]
[{"$nulls":33},"Data cleaned",{"$nulls":6},"x"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed",{"$nulls":6},"x"]
[]
[{"$nulls":33},"Area mapped calculated",{"$nulls":6},"x"]
[{"$nulls":33},"GeoTIFF created and extents recorded",{"$nulls":6},"x"]
[]
[{"$nulls":33},"GSFs exported",{"$nulls":6},"x"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name",{"$nulls":7},"RB2201_058_UTM17N_80m_GEBCO.tif"]
[null,"file location",{"$nulls":7},"Z:\\EM122\\Reference GeoTIFFs\\2022\\RB-22-01_Charleston"]
[]
[null,"N extent of coverage",{"$nulls":7},"31.0118 N x 79.5962 W"]
[null,"S extent of coverage",{"$nulls":7},"25.4111 N x 79.7798 W"]
[]
[]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]

{"sheet":"DN57","index":4,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date",{"$nulls":7},"2022-02-26"]
[null,"Project Number",{"$nulls":6},2201,{"$nulls":12},"Julian Day Number",{"$nulls":7},57]
[null,"Project Name",{"$nulls":6},"Transit to Charlestom",{"$nulls":12},"Local Time Zone",{"$nulls":7},-5]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %",{"$nulls":7},100]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},319.5]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Total Mapped (nm^2)",{"$nulls":7},397.57]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Aprox. Geographical Region",{"$nulls":7},"South of Florida Keys"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28",{"$nulls":12},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC",{"$nulls":12},"Comments",{"$nulls":7},"Eliminated lines 0146-0157 because the data was acquired in shallow water."]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":6},"x",{"$nulls":8},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":6},"x",{"$nulls":8},"Processed in Charlene? (Y/N)",{"$nulls":6},"y",{"$nulls":8},"Finalized surface created",{"$nulls":6},"x"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported",{"$nulls":6},"x"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked",{"$nulls":6},"x"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created",{"$nulls":6},"x"]
[{"$nulls":33},"Data cleaned",{"$nulls":6},"x"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed",{"$nulls":6},"x"]
[]
[{"$nulls":33},"Area mapped calculated",{"$nulls":6},"x"]
[{"$nulls":33},"GeoTIFF created and extents recorded",{"$nulls":6},"x"]
[]
[{"$nulls":33},"GSFs exported",{"$nulls":6},"x"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name",{"$nulls":7},"RB2201_057_UTM17N_80m_GEBCO.tif"]
[null,"file location",{"$nulls":7},"Z:\\EM122\\Reference GeoTIFFs\\2022\\RB-22-01_Charleston"]
[]
[null,"NW extent of coverage",{"$nulls":7},"25.3130 N x 84.1616 W"]
[null,"NE extent of coverage",{"$nulls":7},"25.3254 N x 79.7857 W"]
[null,"S extent of coverage",{"$nulls":7},"23.9847 N x 81.8636 W"]
[]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]

{"sheet":"DN56","index":5,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date",{"$nulls":7},"2022-02-25"]
[null,"Project Number",{"$nulls":6},2201,{"$nulls":12},"Julian Day Number",{"$nulls":7},56]
[null,"Project Name",{"$nulls":6},"Transit to Charlestom",{"$nulls":12},"Local Time Zone",{"$nulls":7},-6]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %",{"$nulls":7},91]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},293.8]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Total Mapped (nm^2)",{"$nulls":7},904.25]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Aprox. Geographical Region",{"$nulls":7},"Pascagoula, MS"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28",{"$nulls":12},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC",{"$nulls":12},"Comments"]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":6},"x",{"$nulls":8},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":6},"x",{"$nulls":8},"Processed in Charlene? (Y/N)",{"$nulls":6},"y",{"$nulls":8},"Finalized surface created",{"$nulls":6},"x"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked",{"$nulls":6},"x"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created",{"$nulls":6},"x"]
[{"$nulls":33},"Data cleaned",{"$nulls":6},"x"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed",{"$nulls":6},"x"]
[]
[{"$nulls":33},"Area mapped calculated",{"$nulls":6},"x"]
[{"$nulls":33},"GeoTIFF created and extents recorded",{"$nulls":6},"x"]
[]
[{"$nulls":33},"GSFs exported",{"$nulls":6},"x"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name",{"$nulls":7},"RB2201_056_UTM16N_80m_GEBCO.tif"]
[null,"file location",{"$nulls":7},"Z:\\EM122\\Reference GeoTIFFs\\2022\\RB-22-01_Charleston"]
[]
[null,"NW extent of coverage",{"$nulls":7},"28.8167 N x 87.0369 W"]
[null,"NE extent of coverage",{"$nulls":7},"N/A"]
[null,"SE extent of coverage",{"$nulls":7},"25.3039 N x 84.0375 W"]
[null,"SW extent of coverage",{"$nulls":7},"N/A"]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]

{"sheet":"DN55","index":6,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date",{"$nulls":7},"2022-02-24"]
[null,"Project Number",{"$nulls":6},2201,{"$nulls":12},"Julian Day Number",{"$nulls":7},55]
[null,"Project Name",{"$nulls":6},"Transit to Charlestom",{"$nulls":12},"Local Time Zone",{"$nulls":7},-6]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %",{"$nulls":7},0]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)",{"$nulls":7},157.9]
[null,"Departure Date",{"$nulls":6},"2022-02-24",{"$nulls":12},"Total Mapped (nm^2)",{"$nulls":7},0]
[null,"Departure Port",{"$nulls":6},"Pascagoula, MS",{"$nulls":12},"Aprox. Geographical Region",{"$nulls":7},"Pascagoula, MS"]
[null,"Arrival Date",{"$nulls":6},"2022-02-28",{"$nulls":12},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":6},"Charleston, SC",{"$nulls":12},"Comments",{"$nulls":7},"Too shallow to turn of the MBES"]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":15},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":15},"Processed in Charlene? (Y/N)",{"$nulls":15},"Finalized surface created"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created"]
[{"$nulls":33},"Data cleaned"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed"]
[]
[{"$nulls":33},"Area mapped calculated"]
[{"$nulls":33},"GeoTIFF created and extents recorded"]
[]
[{"$nulls":33},"GSFs exported"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name"]
[null,"file location"]
[]
[null,"NW extent of coverage"]
[null,"NE extent of coverage"]
[null,"SE extent of coverage"]
[null,"SW extent of coverage"]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]

{"sheet":"YYYY-DDD blank","index":7,"n_rows":54,"n_cols":58,"rows_kept":54,"merged":[[2,1,2,63],[5,1,5,14],[5,21,5,28],[5,29,5,40],[6,1,6,7],[6,8,6,14],[6,21,6,28],[6,29,6,40],[7,1,7,7],[7,8,7,14],[7,21,7,28],[7,29,7,40],[8,1,8,7],[8,8,8,14],[8,21,8,28],[8,29,8,40],[9,1,9,7],[9,8,9,14],[9,21,9,28],[9,29,9,40],[10,1,10,7],[10,8,10,14],[10,21,10,28],[10,29,10,40],[11,1,11,7],[11,8,11,14],[11,21,11,28],[11,29,11,40],[12,1,12,7],[12,8,12,14],[12,21,12,28],[12,29,12,40],[13,1,13,7],[13,8,13,14],[13,21,13,28],[13,29,13,40],[17,1,17,64],[19,1,19,7],[19,9,19,15],[19,17,19,23],[19,25,19,31],[19,33,19,39],[19,41,19,47],[19,49,19,55],[19,57,19,63],[20,1,20,7],[20,17,23,23],[20,24,23,24],[20,25,23,31],[20,33,21,39],[20,40,21,40],[20,41,21,47],[20,49,20,55],[20,57,20,63],[21,49,22,55],[21,56,22,56],[21,57,22,63],[22,33,22,39],[22,41,22,47],[23,33,23,39],[23,41,23,47],[23,49,24,55],[23,56,24,56],[23,57,24,63],[24,33,24,39],[24,41,24,47],[25,33,25,39],[25,41,25,47],[25,49,25,55],[25,57,25,63],[26,33,26,39],[26,41,26,47],[26,49,26,55],[26,57,26,63],[27,33,31,39],[27,40,31,40],[27,41,31,47],[32,33,32,39],[32,41,32,47],[33,33,33,39],[33,41,33,47],[34,33,34,39],[34,41,34,47],[35,33,36,39],[35,40,36,40],[35,41,36,47],[37,33,37,39],[37,41,37,47],[38,33,39,39],[38,40,39,40],[38,41,39,47],[40,33,40,39],[40,41,40,47],[43,1,43,64],[45,1,45,8],[45,9,45,31],[46,1,46,8],[46,9,46,31],[48,1,48,8],[48,9,48,31],[49,1,49,8],[49,9,49,31],[50,1,50,8],[50,9,50,31],[51,1,51,8],[51,9,51,31],[53,1,56,8],[53,9,56,31]]}
[]
[null,"NOAA Ship Ronald H. Brown Working Project Log"]
[null,"          This document is a working project log for hydrographic surveys. This log serves as a checklist and as a repository for notes during the time of the project. The checklist can be used to keep track of the project when multiple people are working on it. These notes are important for compiling information that should be written in the DR.\n          This log also serves as a post-project reference for multibeam coverage. When looking for old data, this log will be a hugely beneficial resource!"]
[]
[null,"General Project Information",{"$nulls":19},"Daily Metrics"]
[null,"NOAA Ship Ronald H. Brown",{"$nulls":19},"UTC Date"]
[null,"Project Number",{"$nulls":19},"Julian Day Number"]
[null,"Project Name",{"$nulls":19},"Local Time Zone"]
[null,"Chief Scientist ",{"$nulls":19},"Multibeam %"]
[null,"Organizations Involved",{"$nulls":19},"Total Distance Traveled (nm)"]
[null,"Departure Date",{"$nulls":19},"Total Mapped (nm^2)"]
[null,"Departure Port",{"$nulls":19},"Aprox. Geographical Region"]
[null,"Arrival Date",{"$nulls":19},"Ops Daily Description"]
[null,"Arrival Port",{"$nulls":19},"Comments"]
[]
[]
[null,"Checklists"]
[null,"          Put an \"x\" in the box next to a task once it has been completed. Once a task is marked as complete, the color will change from red to green."]
[]
[null,"Acquisition",{"$nulls":7},"Comments",{"$nulls":7},"Pre-Processing",{"$nulls":7},"Comments",{"$nulls":7},"Processing",{"$nulls":7},"Comments",{"$nulls":7},"Post-Processing",{"$nulls":7},"Comments"]
[null,"Acquisition log completed",{"$nulls":15},"raw files transferred to appropriate locations on science drive (POS, MBES, SV)",{"$nulls":15},"Processed in Charlene? (Y/N)",{"$nulls":15},"Finalized surface created"]
[{"$nulls":49},"Flier Finder run on finalized surface"]
[{"$nulls":33},"Processed in Caris? (Y/N)"]
[{"$nulls":33},"Lines converted",{"$nulls":15},"Finalized surface run through Grid QA"]
[{"$nulls":33},"Delayed heave applied"]
[{"$nulls":33},"SBET and RMS applied",{"$nulls":15},"BAG exported"]
[{"$nulls":33},"Lines georeferenced",{"$nulls":15},"Bag Checks run"]
[{"$nulls":33},"Transferred raw files, processed files, lines in Caris .hips files, and HSD directory structure checked"]
[]
[]
[]
[]
[{"$nulls":33},"Surface created"]
[{"$nulls":33},"Data cleaned"]
[{"$nulls":33},"Flier Finder run as needed"]
[{"$nulls":33},"Surface recomputed after all cleaning completed"]
[]
[{"$nulls":33},"Area mapped calculated"]
[{"$nulls":33},"GeoTIFF created and extents recorded"]
[]
[{"$nulls":33},"GSFs exported"]
[]
[null,"GeoTIFF"]
[null,"          Insert the GeoTIFF of the day here along with the approximate coordinates of the coverage extents. Also add any notes about the region such as important features, buoys, or moorings."]
[]
[null,"GeoTIFF file name"]
[null,"file location"]
[]
[null,"NW extent of coverage"]
[null,"NE extent of coverage"]
[null,"SE extent of coverage"]
[null,"SW extent of coverage"]
[]
[null,"Important features in region, scientific instruments (moorings, buoys, etc.), or other notes"]